## Project Plan
📊 ProjectPulse AI — Official Project Plan Template
Fill in each row with one task or milestone. Columns marked ★ are REQUIRED for accurate RAG scoring. All date columns must be in DD-MMM-YYYY or YYYY-MM-DD format.
ID | WBS | Task Name ★ | Phase / Milestone | Ancestors | Level | Status ★ | Schedule Health ★ | % Complete ★ | Start Date ★ | End Date ★ | Baseline Start | Baseline Finish ★ | Variance (days) | Total Float (days) ★ | Critical ★ | On Hold | Owner | Assigned To | Status Comment | Predecessors | Budget (USD)
e.g. 1 Unique numeric ID per task row | e.g. 1.1.2 Work Breakdown Structure code (e.g. 1.2.3) | e.g. Design Review Full task or milestone name | e.g. Phase 1: Design High-level phase or milestone grouping | e.g. Project > Phase1 Parent task chain (> separated) | e.g. 2 Hierarchy depth (1=top, 2=sub, etc.) | e.g. In Progress Not Started / In Progress / Completed / On Hold | e.g. Amber Red / Amber / Green — PM's own assessment | e.g. 45 Numeric 0-100 (no % sign needed) | e.g. 01-Jun-2025 Planned start date (DD-MMM-YYYY) | e.g. 30-Sep-2025 Planned end date (DD-MMM-YYYY) | e.g. 01-Jun-2025 Original baseline start before changes | e.g. 30-Sep-2025 Original baseline finish — used for variance | e.g. 5 Positive = late, Negative = ahead | e.g. 0 Scheduling float; 0 or negative = critical risk | e.g. Yes Yes / No — is this on the critical path? | e.g. No Yes / No — is this task currently blocked/paused? | e.g. Alice Smith Responsible person / team | e.g. Bob Jones Individual assignee name | e.g. Pending vendor approval for hardware delivery Free-text PM note about this task's health | e.g. 3,5 Comma-separated IDs of predecessor tasks | e.g. 15000 Planned budget for this task
1 | 1 | PROJECT: E-Commerce Platform Relaunch | Project | Project | 1 | In Progress | Amber | 35 | 01-Jan-2025 | 31-Dec-2025 | 01-Jan-2025 | 31-Dec-2025 | 0 | 10 | No | No | PMO | Jane Doe | Q3 milestone at risk due to vendor delays
2 | 1.1 | Phase 1: Discovery & Requirements | Phase 1 | PROJECT | 2 | Completed | Green | 100 | 01-Jan-2025 | 28-Feb-2025 | 01-Jan-2025 | 28-Feb-2025 | 0 | 20 | No | No | BA Team | Alice Smith
3 | 1.2 | Stakeholder Workshops | Phase 1 | PROJECT > Phase 1 | 3 | Completed | Green | 100 | 01-Jan-2025 | 15-Jan-2025 | 01-Jan-2025 | 15-Jan-2025 | 0 | 0 | Yes | No | Alice Smith | Alice Smith |  | 1 | 3000
4 | 1.3 | Requirements Sign-off | Phase 1 | PROJECT > Phase 1 | 3 | Completed | Green | 100 | 16-Jan-2025 | 28-Feb-2025 | 16-Jan-2025 | 28-Feb-2025 | 0 | 5 | No | No | Alice Smith | Client |  | 3 | 1000
5 | 2 | Phase 2: UI/UX Design | Phase 2 | PROJECT | 2 | In Progress | Amber | 60 | 01-Mar-2025 | 30-May-2025 | 01-Mar-2025 | 30-Apr-2025 | 30 | 0 | Yes | No | Design Lead | Bob Jones | Delayed due to 2 rounds of client revisions | 4 | 12000
6 | 2.1 | Wireframes & Prototypes | Phase 2 | PROJECT > Phase 2 | 3 | Completed | Green | 100 | 01-Mar-2025 | 31-Mar-2025 | 01-Mar-2025 | 31-Mar-2025 | 0 | 10 | No | No | Bob Jones | Bob Jones |  | 4 | 5000
7 | 2.2 | High-Fidelity Mockups | Phase 2 | PROJECT > Phase 2 | 3 | In Progress | Red | 40 | 01-Apr-2025 | 30-May-2025 | 01-Apr-2025 | 30-Apr-2025 | 30 | 0 | Yes | No | Bob Jones | Carol Lee | BLOCKED: Client feedback not received on time | 6 | 7000
8 | 3 | Phase 3: Backend Development | Phase 3 | PROJECT | 2 | In Progress | Green | 55 | 01-Apr-2025 | 31-Jul-2025 | 01-Apr-2025 | 31-Jul-2025 | 0 | 8 | Yes | No | Dev Lead | Dev Team |  | 5 | 45000
9 | 3.1 | API Gateway Setup | Phase 3 | PROJECT > Phase 3 | 3 | Completed | Green | 100 | 01-Apr-2025 | 30-Apr-2025 | 01-Apr-2025 | 30-Apr-2025 | 0 | 12 | No | No | Sam Patel | Sam Patel |  | 5 | 8000
10 | 3.2 | Core Services Development | Phase 3 | PROJECT > Phase 3 | 3 | In Progress | Amber | 45 | 01-May-2025 | 31-Jul-2025 | 01-May-2025 | 30-Jun-2025 | 31 | -2 | Yes | No | Sam Patel | Dev Team | Pending vendor API documentation delivery | 9 | 22000

## Column Reference Guide
ProjectPulse AI — Column Reference Guide
This guide explains every column, whether it is required, which signal it feeds, and what values are accepted.
Column Name | Required? | Signal It Feeds | Accepted Values | Format | Example | Notes
Task Name | ★ YES | All signals | Any text | Text | Design Review | Must be non-empty. Used as the primary task identifier.
Status | ★ YES | Schedule Slippage, Blockers | Not Started / In Progress / Completed / On Hold | Dropdown list | In Progress | Used to detect stalled or blocked tasks.
Schedule Health | ★ YES | Schedule Slippage (30%) | Red / Amber / Green / Yellow | Text / Dropdown | Amber | Core signal. PM's own assessment of schedule status.
% Complete | ★ YES | Progress Gap (20%) | 0 to 100 (numeric, no % sign) | Number | 45 | Compared to expected linear progress based on timeline.
Start Date | ★ YES | Progress Gap, Schedule | Any date | DD-MMM-YYYY | 01-Jun-2025 | Used to calculate elapsed time and expected progress.
End Date | ★ YES | Progress Gap, Schedule | Any date | DD-MMM-YYYY | 30-Sep-2025 | Planned completion date.
Baseline Finish | ★ YES | Milestone Health (20%) | Any date | DD-MMM-YYYY | 30-Sep-2025 | Original committed finish. Used to detect milestone slippage.
Total Float | ★ YES | Blockers & Critical (15%) | Integer (negative means overdue) | Number (days) | 0 | Negative float flags critical path risk. Key override trigger.
Critical | ★ YES | Blockers & Critical (15%) | Yes / No | Dropdown | Yes | Tasks on the critical path. Key override trigger.
Status Comment | Optional | Stakeholder Sentiment (10%) | Free text | Text | Pending vendor approval | PM notes. Scanned for blocker keywords and sentiment.
Phase / Milestone | Optional | Milestone Health (20%) | Any text | Text | Phase 2: Design | Groups tasks into phases. Helps milestone health scoring.
Baseline Start | Optional | Milestone Health | Any date | DD-MMM-YYYY | 01-Jun-2025 | Used alongside Baseline Finish for variance calculation.
Variance (days) | Optional | Schedule Slippage | Integer | Number (days) | 15 | Positive = late. Auto-calculated if not provided.
On Hold | Optional | Blockers | Yes / No | Dropdown | No | Flags paused/blocked tasks.
Owner | Optional | (Metadata only) | Name or team | Text | Alice Smith | For reporting display only. Not used in scoring.
Assigned To | Optional | (Metadata only) | Name | Text | Bob Jones | For reporting display only. Not used in scoring.
Predecessors | Optional | Blockers | Comma-separated task IDs | e.g. 3,5 | 3,5 | Helps detect dependency chain blockers.
Budget (USD) | Optional | Budget Burn (5%) | Numeric amount | Number | 15000 | If absent for any task, budget signal is excluded and weights are renormalized.
WBS | Optional | (Metadata only) | Dot-separated code | e.g. 1.2.3 | 1.2.3 | Work breakdown structure code for hierarchy.
Ancestors | Optional | (Hierarchy detection) | Parent names separated by > | Text | Project > Phase 1 | Alternative hierarchy indicator. Used if Level is not provided.
Level | Optional | (Hierarchy detection) | Integer (1=top level) | Number | 2 | Explicit depth in task tree. If missing, inferred from Ancestors.
ID | Optional | (Row tracking) | Any unique value | Number or text | 1 | Used for predecessor references. Auto-assigned if missing.

## RAG Guide & Tips
ProjectPulse AI — RAG Scoring Guide & Tips
RAG STATUS THRESHOLDS
Score Range | Status & Meaning
0 – 34 | 🟢 GREEN — Project is on track. No critical overrides triggered. Data quality sufficient.
35 – 69 | 🟡 AMBER — Watch-list. Minor delays, progress gaps, or warning signals detected.
70 – 100 | 🔴 RED — Critical. Significant delays, blocked milestones, or override rules triggered.
CRITICAL OVERRIDE RULES (These force RED regardless of score)
Rule 1 | A critical path task is delayed by more than 15 working days.
Rule 2 | A key milestone missed its baseline finish date by more than 30 days.
Rule 3 | More than 3 tasks flagged as Blocked or On Hold simultaneously.
Rule 4 | Over 40% of active tasks show Red or Yellow Schedule Health.
TIPS FOR BEST RESULTS
Tip 1 | Always fill in Baseline Finish. Without it, milestone health scoring is skipped.
Tip 2 | Use the Schedule Health dropdown exactly: Red / Amber / Green. Typos are ignored.
Tip 3 | Status Comment is powerful — write meaningful PM notes (e.g. 'Pending vendor approval for hardware'). The AI reads these.
Tip 4 | Fill in Total Float for every task. Negative values are the strongest single indicator of schedule risk.
Tip 5 | Mark Critical = Yes for any task on the critical path, not just the last task in the chain.
Tip 6 | You can upload multiple project files at once. Each file becomes one snapshot in the portfolio.
Tip 7 | Re-uploading an updated plan creates a new snapshot — old snapshots are preserved for trend tracking.