## Slide 1
PROJECT PORTFOLIO HEALTH SYNTHESIS
Monthly Executive Performance Review & Automated RAG Analysis
Generated by Project Health AI Agent | Date: 2026-08-11
ON TRACK / GREEN
1
Projects executing smoothly against baseline schedule and budget expectations.
UNDER WATCH / AMBER
0
Projects exhibiting minor delays, progress gaps, or warning indicators.
CRITICAL ESCALATE / RED
2
Projects with significant delays, blocked milestones, or high risk items.
Zycus Project Health reporting agent | Confidential
Slide 1 of 6

## Slide 2
PORTFOLIO SUMMARY
Portfolio Health Directory
Consolidated view of active project stages, scores, and data confidence
Project Name | RAG Status | RAG Score | Data Quality | Current Stage | Project Manager
1.0 Platform Migration Project (Project_Alpha_Week3) | Red | 83.1/100 | 90% | Unknown | Unknown
1.0 Platform Migration Project (Project_Alpha_Week2) | Red | 71.1/100 | 90% | Unknown | Unknown
1.0 Platform Migration Project | Green | 26.2/100 | 90% | Unknown | Unknown
Zycus Project Health reporting agent | Confidential
Slide 2 of 6

## Slide 3
PORTFOLIO SUMMARY
Portfolio Narrative & Sentiment Summary
Consolidated AI summaries and stakeholder sentiment comments across all projects
PORTFOLIO EXECUTIVE NARRATIVES
• 1.0 Platform Migration Project (Project_Alpha_Week3) (Red): The project's RAG status is Red, primarily due to 5 red and 0 amber/yellow schedule-health rows (source_row numbers 2, 4, 5, 6, 7), indicating significant sched...
• 1.0 Platform Migration Project (Project_Alpha_Week2) (Red): The project's RAG status is Red, primarily due to schedule health issues (source_row 2, 4, 5) and a progress gap of 13.1 points behind the expected timeline. Th...
• 1.0 Platform Migration Project (Green): The project's RAG status is Green, with a score of 26.2 and high confidence, as seen in the deterministic_rag section (source_row not applicable). The top signa...
STAKEHOLDER SENTIMENT & THEMES
• 1.0 Platform Migration Project (Project_Alpha_Week3): No comments available
Key Risk Themes: Schedule Risks, Blocker Risks, Progress Delays
• 1.0 Platform Migration Project (Project_Alpha_Week2): No comments available.
Key Risk Themes: Schedule Delays, Blocker Tasks, Progress Gap
• 1.0 Platform Migration Project: No comments available
Key Risk Themes: Schedule Delays, Progress Gaps, Lack of Milestone Data
Zycus Project Health reporting agent | Confidential
Slide 3 of 6

## Slide 4
PORTFOLIO SUMMARY
Emerging Systemic Risks & Signal Analysis
Critical task slippages and cross-project signal alert distributions
TOP DELIVERY RISKS & CRITICAL TASK EVIDENCE
• 1.0 Platform Migration Project (Project_Alpha_Week3) (Row 2): 1.0 Platform Migration Project
Status: In Progress | Health: Red | Float: -20.0d | Comp: 60.0%
• 1.0 Platform Migration Project (Project_Alpha_Week3) (Row 6): 1.4 Integration Testing
Status: Not Started | Health: Red | Float: -20.0d | Comp: 0%
• 1.0 Platform Migration Project (Project_Alpha_Week3) (Row 7): MILESTONE: Design Sign-off
Status: Missed | Health: Red | Float: -20.0d | Comp: 0%
• 1.0 Platform Migration Project (Project_Alpha_Week3) (Row 5): 1.3 Dev Environment Setup
Status: On Hold | Health: Red | Float: -18.0d | Comp: 0%
• 1.0 Platform Migration Project (Project_Alpha_Week3) (Row 4): 1.2 Architecture Design
Status: In Progress | Health: Red | Float: -15.0d | Comp: 70.0%
ELEVATED SIGNAL & FLIP ALERTS
• No recent RAG status flips detected.
PORTFOLIO SIGNAL ALERT FREQUENCY:
• schedule: Elevated in 1 project(s)
Zycus Project Health reporting agent | Confidential
Slide 4 of 6

## Slide 5
PORTFOLIO SUMMARY
Recommended Leadership & Escalation Actions
Immediate interventions for at-risk projects and general portfolio quality recommendations
IMMEDIATE PROJECT ESCALATIONS
• 1.0 Platform Migration Project (Project_Alpha_Week3) (Red): Run a schedule recovery review focused on red/yellow rows and near-term milestones
• 1.0 Platform Migration Project (Project_Alpha_Week3) (Red): Create an escalation list for critical-path, pending, and dependency-driven blockers
• 1.0 Platform Migration Project (Project_Alpha_Week3) (Red): Develop a plan to address the 6.1 point progress gap
• 1.0 Platform Migration Project (Project_Alpha_Week3) (Red): Identify and mitigate risks associated with critical path tasks
GENERAL PORTFOLIO GOVERNANCE
• Enforce Weekly Baseline Syncs: Ensure all project managers update schedule baselines weekly to maintain high-quality tracking metrics.
• Address Critical Negative Float: Conduct dedicated review sessions for tasks exhibiting negative float to resolve blockers before milestone slips occur.
• Refine Commenting Standard: Ensure PM comment updates describe concrete mitigation steps rather than status summaries to keep sentiment scores clear.
• Verify Workbook Data Quality: Fix missing ownership and baseline dates inside source spreadsheets to increase data quality confidence scores.
• Establish Trend Milestones: Leverage SQLite time-series data to compare current month trends against baseline trajectory projections.
Zycus Project Health reporting agent | Confidential
Slide 5 of 6

## Slide 6
HOW PROJECT WORKS
How Project Works: RAG Engine & Problem-Solving
Standard RAG signal weights, automatic normalization, and decision auditability
DETERMINISTIC RAG LOGIC MODEL
• Schedule Health (30%): Evaluates task delays, late critical paths, float erosion.
• Progress Gap (20%): Compares actual % complete vs expected progress by date.
• Milestones Confidence (20%): Measures completed vs delayed key milestones.
• Blocker Keywords (15%): Scans task names and status comments for blocker keywords.
• Stakeholder Sentiment (10%): NLP-analyzed tone and outlook of weekly PM comments.
• Budget Variance (5%): Burn rates and cost variance (omitted if data is absent).
Critical Override Rules:
If any critical task has a Red schedule health and is either root-level or at-risk level is High, the overall project status is forced to Red regardless of other signals. Ensures major threats are never hidden.
EFFICIENCY & PROBLEM-SOLVING
• Eliminating Reporting Bias: Replaces subjective/manual project health reporting with automated, uniform, data-driven evaluation.
• Automatic Data Normalization: Cleans and parses diverse Excel formats. Automatically infers active project stages from task hierarchies and dates.
• Uncompromised Auditability: Every AI narrative and signal cites precise Excel row numbers, allowing stakeholders to trace results directly back to the sheet.
• Resilient Fallbacks: Missing baseline dates default to current dates; missing comments default to a neutral sentiment score, ensuring the pipeline never fails.
• Historical Persistence: Stores all weekly runs in a unified SQLite database, enabling trend analytics and automated RAG flip alerts.
Zycus Project Health reporting agent | Confidential
Slide 6 of 6