## Project Plan
Task Name | Status | % Complete | Start Date | End Date | Baseline Start | Baseline Finish | Total Float | Critical | Schedule Health | Owner | Comments | Phase / Milestone
Platform Migration Project | In Progress | 52 | 2026-06-12 | 2026-10-25 | 2026-06-12 | 2026-10-10 | -8 | TRUE | Amber | Alice | Project slipping. Vendor delayed Phase 2 kickoff by 2 weeks.
1.1 Requirements & Scoping | Completed | 100 | 2026-06-12 | 2026-07-02 | 2026-06-12 | 2026-07-02 | 8 | FALSE | Green | Alice | Complete.
1.2 Architecture Design | Completed | 100 | 2026-07-03 | 2026-07-22 | 2026-07-03 | 2026-07-22 | 6 | FALSE | Green | Bob | Complete.
1.3 Dev Environment Setup | In Progress | 80 | 2026-07-23 | 2026-08-23 | 2026-07-23 | 2026-08-16 | -4 | TRUE | Amber | Carol | Vendor feedback delayed sign-off. Blocked on external dependency.
1.4 Core Module Development | Not Started | 0 | 2026-08-24 | 2026-09-30 | 2026-08-17 | 2026-09-20 | -8 | TRUE | Amber | Dave | Delayed due to environment setup overrun.
MILESTONE: Phase 1 Sign-off | Delayed | 0 | 2026-08-23 | 2026-08-23 | 2026-08-16 | 2026-08-16 | -7 | TRUE | Amber | Alice | Missed original milestone date. | Milestone