## Summary
Project Summary Dashboard
Project Name | Zycus - Red Implementation
Project Manager | Alice Johnson
Project Start Date | 2026-05-09
Project End Date | 2026-11-05
Project Stage | Build & Configuration Phase
At Risk | High
% Complete | 0.2
Schedule Health | Red
Today's Date | 2026-07-08
Duration | 180
Project Status | In Progress

## Project Plan
Level | Task Name | Status | % Complete | Schedule Health | Start Date | End Date | Baseline Start | Baseline Finish | Critical ? | Total Float | Comments | Project Manager
0 | Zycus - Red Implementation Project | In Progress | 20% | Red | 2026-05-09 | 2026-11-05 | 2026-05-09 | 2026-11-05 | Yes | -15 | Significant delays across integration and testing start. Project is severely at risk. | Alice Johnson
1 | Design & Blueprint Phase | Completed | 100% | Yellow | 2026-05-09 | 2026-06-18 | 2026-05-09 | 2026-05-29 | No | -10 | Completed 20 days late | Alice Johnson
1 | Build & Configuration Phase | In Progress | 25% | Red | 2026-06-18 | 2026-07-28 | 2026-05-29 | 2026-07-18 | Yes | -18 | Build is blocked by integration failures | Alice Johnson
2 | Core S2P Configuration | In Progress | 35% | Red | 2026-06-18 | 2026-07-03 | 2026-05-29 | 2026-06-23 | Yes | -15 | Late active task. Blocked on middleware server setup. | Alice Johnson
2 | ERP Integration Mapping | In Progress | 10% | Red | 2026-06-23 | 2026-07-07 | 2026-06-08 | 2026-07-03 | Yes | -20 | Late active task. Blocked on network credentials and ports. | Alice Johnson
2 | UAT Script Writing | In Progress | 10% | Yellow | 2026-06-28 | 2026-07-18 | 2026-06-18 | 2026-07-13 | No | -12 | Scripts are delayed as configuration isn't completed. | Alice Johnson
1 | Testing & UAT Phase | Not Started | 0% | Red | 2026-07-06 | 2026-08-17 | 2026-06-28 | 2026-08-07 | Yes | -18 | UAT launch missed start date by 2 days. | Alice Johnson

## Comments
Reference Row | Comment Text | Author | Created At
Row 4 | Severe blocker: Integration with client JDE system is failing. Client has not opened necessary firewall ports. | Alice Johnson | 2026-07-08
Row 5 | Network ports still blocked. Escalate to VP for network credentials. | Alice Johnson | 2026-07-07