## Summary
Project Summary Dashboard
Project Name | Zycus - Amber Implementation
Project Manager | John Smith
Project Start Date | 2026-05-09
Project End Date | 2026-11-05
Project Stage | Build & Configuration Phase
At Risk | Medium
% Complete | 0.45
Schedule Health | Amber
Today's Date | 2026-07-08
Duration | 180
Project Status | In Progress

## Project Plan
Level | Task Name | Status | % Complete | Schedule Health | Start Date | End Date | Baseline Start | Baseline Finish | Critical ? | Total Float | Comments | Project Manager
0 | Zycus - Amber Implementation Project | In Progress | 45% | Amber | 2026-05-09 | 2026-11-05 | 2026-05-09 | 2026-11-05 | Yes | 0 | Experiencing minor delays in Integration configuration | John Smith
1 | Design & Blueprint Phase | Completed | 100% | Green | 2026-05-09 | 2026-06-08 | 2026-05-09 | 2026-06-08 | No | 0 | Completed on time | John Smith
1 | Build & Configuration Phase | In Progress | 50% | Yellow | 2026-06-08 | 2026-08-07 | 2026-06-08 | 2026-08-07 | Yes | -2 | Integration delays with Client ERP | John Smith
2 | Core S2P Configuration | Completed | 100% | Green | 2026-06-08 | 2026-07-03 | 2026-06-08 | 2026-07-03 | Yes | 0 | Completed config | John Smith
2 | ERP Integration Mapping | In Progress | 40% | Red | 2026-06-18 | 2026-07-06 | 2026-06-18 | 2026-07-06 | Yes | -5 | Late active task due to API schema change from client ERP. | John Smith
2 | Data Migration Setup | In Progress | 30% | Yellow | 2026-06-28 | 2026-08-07 | 2026-06-28 | 2026-08-07 | No | 5 | Minor delay on master data upload | John Smith
1 | Testing & UAT Phase | Not Started |  |  | 2026-08-08 | 2026-09-21 | 2026-08-08 | 2026-09-21 | No | 5 | Planned | John Smith

## Comments
Reference Row | Comment Text | Author | Created At
Row 6 | ERP integration has hit a slight dependency block. We need the client ERP specialist to confirm the API headers. | John Smith | 2026-07-08
Row 7 | Master data templates have been shared. Clean up is pending from client side. | John Smith | 2026-07-06