## Summary
Project Summary Dashboard
Project Name | Zycus - Green Implementation
Project Manager | Jane Doe
Project Start Date | 2026-05-09
Project End Date | 2026-11-05
Project Stage | Build & Configuration Phase
At Risk | Low
% Complete | 0.6
Schedule Health | Green
Today's Date | 2026-07-08
Duration | 180
Project Status | In Progress

## Project Plan
Level | Task Name | Status | % Complete | Schedule Health | Start Date | End Date | Baseline Start | Baseline Finish | Critical ? | Total Float | Comments | Project Manager
0 | Zycus - Green Implementation Project | In Progress | 60% | Green | 2026-05-09 | 2026-11-05 | 2026-05-09 | 2026-11-05 | Yes | 10 | On track, smooth progress | Jane Doe
1 | Design & Blueprint Phase | Completed | 100% | Green | 2026-05-09 | 2026-06-08 | 2026-05-09 | 2026-06-08 | No | 0 | Completed on time | Jane Doe
2 | Requirement Workshops | Completed | 100% | Green | 2026-05-09 | 2026-05-24 | 2026-05-09 | 2026-05-24 | No | 0 | Sign-off obtained | Jane Doe
2 | Design Document Sign-off | Completed | 100% | Green | 2026-05-24 | 2026-06-08 | 2026-05-24 | 2026-06-08 | No | 0 | Blueprint approved | Jane Doe
1 | Build & Configuration Phase | In Progress | 70% | Green | 2026-06-08 | 2026-08-07 | 2026-06-08 | 2026-08-07 | Yes | 5 | Build is moving smoothly | Jane Doe
2 | Core S2P Configuration | In Progress | 85% | Green | 2026-06-08 | 2026-07-18 | 2026-06-08 | 2026-07-18 | Yes | 5 | Configurations on track | Jane Doe
2 | Integration Setup | In Progress | 40% | Green | 2026-07-09 | 2026-08-07 | 2026-07-09 | 2026-08-07 | Yes | 12 | APIs are mapped | Jane Doe
1 | Testing & UAT Phase | Not Started |  |  | 2026-08-08 | 2026-09-21 | 2026-08-08 | 2026-09-21 | No | 15 | Preparation started | Jane Doe
1 | Go-Live Preparation | Not Started |  |  | 2026-09-22 | 2026-11-05 | 2026-09-22 | 2026-11-05 | No | 20 | Planned | Jane Doe

## Comments
Reference Row | Comment Text | Author | Created At
Row 2 | Project dashboard updated, status remains green. Team is executing blueprint items as scheduled. | Jane Doe | 2026-07-08
Row 6 | Core S2P config is nearing completion. Client team has approved early testing. | Jane Doe | 2026-07-05