Created with an evaluation copy of Aspose.Words. To remove all limitations, you can use Free Temporary License https://products.aspose.com/words/temporary-license/

# How Project Works

This document defines the methodology, features, technology stack, and data processing workflows for the Project Health Reporting Agent. It explains how the project works end-to-end, the systemic architecture, and the precise rule engine methodology.

## 1. RAG Determination Methodology (How the Engine Works)

The core philosophy of the system is deterministic, auditable scoring. Instead of delegating RAG classification to black-box LLMs—which are susceptible to hallucination, inconsistency, and lack mathematical validation—the RAG classification is computed via a structured rule engine. The LLM acts as an explanatory and summarization layer on top of the verified metrics.

+------------------+     +------------------------+     +-------------------------+
|  Excel Workbook  | --> | Deterministic Engine   | --> |      LLM Agent          |
|  (Raw Task Data) |     | (Weights & Overrides)  |     | (Narratives/Sentiment)  |
+------------------+     +------------------------+     +-------------------------+
                                                                     |
                                                                     v
                                                        +-------------------------+
                                                        | SQLite Snapshot Storage |
                                                        +-------------------------+

### 1.1 Weighted Signals

Every project snapshot is evaluated across six foundational signal layers. Each signal yields a normalized score between 0 (lowest risk) and 100 (highest risk).

| Signal | Weight | Computation Logic |
| --- | --- | --- |
| Schedule Slippage | 30% | Scans the schedule health column for explicit "Red", "Amber", or "Yellow" flags; checks total float erosion; and scores late active tasks. |
| Progress Gap | 20% | Compares actual percent complete against the expected progress linearly calculated from the elapsed project timeline. |
| Milestone Health | 20% | Analyzes incomplete key milestones, measuring the ratio of delayed or high-risk milestones to completed ones. |
| Blockers & Critical Path | 15% | Identifies tasks on the critical path, negative total float, and checks task comments/predecessors for blocker keywords (e.g., blocked, pending, delay). |
| Stakeholder Sentiment | 10% | Evaluates the emotional tone, outlook, and thematic urgency of PM comments on a scale from 0 to 100. |
| Budget Burn | 5% | Calculates cost variance and burn rates. If budget metrics are missing from the plan, this signal is excluded, and weights are re-normalized. |

### 1.2 Scoring Normalization Formula

The overall project health score ($S_{project}$) is calculated as: $$S_{project} = \frac{\sum_{i} W_i \cdot S_i}{\sum_{i} W_i}$$ Where $W_i$ is the weight of signal $i$, and $S_i$ is the normalized score of signal $i$. If a signal is unavailable (e.g., budget data is absent), its weight $W_i$ is set to zero, and the remaining weights are re-normalized to sum to $1.0$.

### 1.3 RAG Status Mapping

The final score ($S_{project}$) maps to a status:

- 🟢 Green: $0 \le S_{project} < 35$ (No critical overrides triggered)

- 🟡 Amber: $35 \le S_{project} < 70$

- 🔴 Red: $70 \le S_{project} \le 100$

### 1.4 Critical Override Rules

To capture severe systemic risks that a weighted average might dilute, the engine applies deterministic override rules to force a project to Red:

- Severe Critical Path Delay: An uncompleted critical path task delayed by more than 15 working days.

- Milestone Failure: A key milestone that has missed its baseline finish date by more than 30 days and remains incomplete.

- Multiple Blockers: More than 3 active tasks flag-marked as blocked by external dependencies.

- Widespread Red Schedule: Over 40% of active tasks flagged as "Red" or "Yellow" schedule health in the workbook.

## 2. Technical Stack Methodology

The architecture utilizes a decoupled client-server model designed for performance, local deployability, and robust offline operations. The separation of concerns ensures that the AI reasoning layers are independent of the deterministic data parsing components.

+---------------------------------------------+
       |             Vite/React Client               |
       |               (Port 3000)                   |
       +---------------------------------------------+
                              ▲
                              │ REST API (JSON)
                              ▼
       +---------------------------------------------+
       |             FastAPI Server                  |
       |               (Port 8001)                   |
       +---------------------------------------------+
            │                      │             │
            ▼                      ▼             ▼
      +-----------+         +------------+  +-----------+
      |  SQLite   |         |    Groq    |  | python-   |
      | Database  |         |  LLM API   |  |   pptx    |
      +-----------+         +------------+  +-----------+

### 2.1 Backend Core

- Language: Python 3.10+ (Static type annotations enforced). Python was chosen for its robust data manipulation libraries and AI integration capabilities.

- REST API: FastAPI + Uvicorn (Bound to Port 8001 to bypass default port conflicts). Provides high-performance async endpoints for the frontend.

- Database: SQLite (sqlite3 with row factory enabled) to persist project metadata, task attributes, RAG signals, comments, and quality metrics. Chosen for its zero-configuration local storage.

- AI reasoning: Groq client accessing llama-3.3-70b-versatile (or fallback Google Gemini API / OpenAI API) via a structured JSON-schema tool-calling interface. This provides the intelligence layer for synthesizing project narratives.

- Excel Engine: openpyxl with custom memory loading and explicit handle disposal to prevent file locks on Windows environments.

- Slide Engine: python-pptx implementing automated layout coordinate grids and font color normalization to produce executive monthly presentations.

### 2.2 Frontend Client

- Framework: React 19 + TypeScript + Vite. Provides a highly responsive user interface with strict type safety.

- Routing: TanStack Router (Typesafe routes).

- Styling: Tailwind CSS + Shadcn UI primitive blocks. Ensures a modern, accessible, and cohesive design system.

- Icons: Lucide React.

- State Management: React Query (TanStack Query) for declarative caching and optimistic mutations, managing data fetching from the FastAPI backend.

## 3. Product Features

The system features are designed to create a seamless pipeline from raw data to executive insight:

- Resilient Excel Ingestion: Reads multi-sheet Excel files. Reconstructs hierarchies dynamically using indentation levels or Ancestors values, normalizing disparate date formats, null values, and custom fields.

- Active Stage Auto-Detection: If a project stage is missing from the workbook summary, the system automatically walks the task hierarchy tree to determine the current, incomplete phase.

- Interactive RAG Explanations: A dedicated dashboard tab ("Why this status") displays the reasoning behind the RAG status, listing the triggering signal details and override indicators.

- Audit Trails: The "Signals" tab provides a breakdown of every computed signal (weights, raw values, normalized risk scores, and evidence).

- Raw Data Preservation: Under "Preserved Attributes", users can inspect every original column value parsed from the workbook, ensuring no information is discarded.

- Project Switcher: A header dropdown selector lets users switch between different projects within the portfolio, updating all tabs dynamically.

- Cascade Snapshot Deletion: Users can delete any uploaded snapshot. The system performs cascade deletions across SQLite tables, unlinks Markdown reports, and cleans up orphaned project directories.

- Executive Slides Generation: Compiles monthly summaries into a 16:9 widescreen presentation deck using the RAG logic and AI insights.

## 4. End-to-End Data Lifecycle (How It Works in Practice)

- File Upload: The user uploads an .xlsx file via the frontend dropzone.

- Parsing & Normalization: The backend reads the file, cleans cells, assigns unique row numbers, and saves the hierarchy.

- Signal Extraction: The backend's deterministic engine computes metrics for slip, progress gap, milestones, blockers, and sentiment.

- AI Synthesis: The computed signals and key task rows are packaged into a structured prompt. The LLM processes this context and returns narrative summaries explaining why the metrics look the way they do.

- Storage: The workbook structure, raw data, computed signals, RAG status, and AI summaries are saved as a new snapshot in the SQLite database.

- Presentation: The frontend queries the REST API to load snapshots, display the dashboard, or trigger PowerPoint slide compilation for monthly reporting.