## Project Plan
Task Name | Status | % Complete | Start Date | End Date | Baseline Start | Baseline Finish | Total Float | Critical | Schedule Health | Owner | Comments | Phase / Milestone
Platform Migration Project | In Progress | 55 | 2026-06-12 | 2026-11-09 | 2026-06-12 | 2026-10-10 | -22 | TRUE | Red | Alice | Le projet est sérieusement en danger. Les problèmes budgétaires et les retards du fournisseur mettent en péril les livrables clés. Une décision de direction est urgente.
1.1 Requirements & Scoping | Completed | 100 | 2026-06-12 | 2026-07-02 | 2026-06-12 | 2026-07-02 | 0 | FALSE | Green | Alice | Terminé.
1.2 Architecture Design | Completed | 100 | 2026-07-03 | 2026-07-22 | 2026-07-03 | 2026-07-22 | 0 | FALSE | Green | Bob | Complete.
1.3 Dev Environment Setup | On Hold | 80 | 2026-07-23 | 2026-09-05 | 2026-07-23 | 2026-08-16 | -18 | TRUE | Red | Carol | BLOCKED — vendor contract terminated unexpectedly. Cannot proceed without a replacement partner.
1.4 Core Module Development | Not Started | 0 | 2026-09-05 | 2026-10-20 | 2026-08-17 | 2026-09-20 | -22 | TRUE | Red | Dave | Cannot start. Predecessor is on hold. Risk of full programme delay.
1.5 Integration Testing | Not Started | 0 | 2026-10-20 | 2026-11-19 | 2026-09-20 | 2026-10-20 | -30 | TRUE | Red | Eve | Not scheduled. Critical path at risk of 30+ day slip.
MILESTONE: Phase 1 Sign-off | Missed | 0 | 2026-08-06 | 2026-08-06 | 2026-08-16 | 2026-08-16 | -30 | TRUE | Red | Alice | Milestone was missed. Requires board-level escalation. | Milestone