## Project Plan
Task Name | Status | % Complete | Start Date | End Date | Baseline Start | Baseline Finish | Total Float | Critical | Schedule Health | Owner | Comments | Phase / Milestone
Platform Migration Project | In Progress | 45 | 2026-06-12 | 2026-10-10 | 2026-06-12 | 2026-10-10 | 12 | FALSE | Green | Alice | Project on track. All milestones met so far.
1.1 Requirements & Scoping | Completed | 100 | 2026-06-12 | 2026-07-02 | 2026-06-12 | 2026-07-02 | 8 | FALSE | Green | Alice | Completed two days ahead of schedule.
1.2 Architecture Design | Completed | 100 | 2026-07-03 | 2026-07-22 | 2026-07-03 | 2026-07-22 | 6 | FALSE | Green | Bob | Design approved by all stakeholders.
1.3 Dev Environment Setup | In Progress | 60 | 2026-07-23 | 2026-08-16 | 2026-07-23 | 2026-08-16 | 5 | FALSE | Green | Carol | Progressing. 60% done.
1.4 Core Module Development | Not Started | 0 | 2026-08-17 | 2026-09-20 | 2026-08-17 | 2026-09-20 | 8 | FALSE | Green | Dave | Ready to start after environment sign-off.
MILESTONE: Phase 1 Sign-off | Not Started | 0 | 2026-08-16 | 2026-08-16 | 2026-08-16 | 2026-08-16 | 0 | FALSE | Green | Alice |  | Milestone