## Project Plan
Task Name | Status | % Complete | Start Date | End Date | Baseline Start | Baseline Finish | Total Float | Critical | Schedule Health | Owner | Comments | Phase / Milestone
Cloud Security Compliance | In Progress | 70 | 2026-05-13 | 2026-09-10 | 2026-05-13 | 2026-09-10 | 15 | FALSE | Green | Frank | All compliance controls on track. Final audit in 4 weeks.
2.1 Risk Assessment | Completed | 100 | 2026-05-13 | 2026-06-12 | 2026-05-13 | 2026-06-12 | 10 | FALSE | Green | Frank | Risk register approved.
2.2 Policy Framework | Completed | 100 | 2026-06-13 | 2026-07-12 | 2026-06-13 | 2026-07-12 | 8 | FALSE | Green | Grace | All 47 policies signed off.
2.3 Technical Controls Implementation | In Progress | 65 | 2026-07-13 | 2026-08-21 | 2026-07-13 | 2026-08-21 | 6 | FALSE | Green | Hank | Controls deployment is 65% complete.
2.4 External Audit Preparation | Not Started | 0 | 2026-08-22 | 2026-09-10 | 2026-08-22 | 2026-09-10 | 15 | FALSE | Green | Frank | Audit pack in progress.
MILESTONE: ISO 27001 Audit | Not Started | 0 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 0 | FALSE | Green | Frank |  | Milestone